| 2018 UGVR Program Timeline |
| --- |
| Date | Tasks |
| Oct., 2017 | Evaluation and planning |
| Oct 20, 2017 | UGVR program announcement to SU faculty |
| Nov 20, 2017 | SU CPM updates the UGVR MOU and obtains consensus from partner universities. |
| Nov 30, 2017 | SU CPM collects position descriptions from host faculty, organizes and sends them to partner universities. |
| Jan 10, 2018 | Partner universities collect applications and pre-select candidates. Each school chooses up-to-3 students for each position and sends applications to SU CPM. |
| Feb 15, 2018 | SU faculty members review application materials and make final decisions. SU CPM Sends DS-7002 forms to host faculty members to fill. |
| Feb 25, 2018 | SU CPM coordinates the process and sends selection results to partner universities. Collects DS-7002 forms from host faculty. |
| March 10, 2018 | Students make decision and give acceptance confirmation. Partner universities collect application forms and passport copies and submit to SU CPM. |
| March 15, 2018 | SU CPM sends DS-7002 forms for confirmed students to sign. SU CPM prepares official invitation letter and submits application packages to Registrar’s Office for approval. |
| April 30, 2018 | SU CPM obtains SU ID#s for UGVR students. Submit application to Bechtel for SEVIS DS-2019 forms. Send UGVR students official invitation letters, DS-2019 forms, and DS-7002 forms. |
| May 15, 2018 | Pre-trip orientation (may have it done remotely collaborated with partner universities). UGVR students go for US visa application and interviews. |
| May 31, 2018 | Make room reservations for orientation, reception, workshops and poster session on campus. Invite faculty director and deans. |
| Late May/June, 2018 | Travel arrangement and logistics. |
| July 2-Sept 1, 2018 | UGVR students conduct summer research at Stanford |
| Sept 30, 2018 | SU CPM coordinates and helps with program certificate letters. Collects boarding passes and other required docs from the students. Conduct program survey with participating faculty and students. |

Stanford Calendar:

- Autumn 2017-18: September 25 and December 15

- Winter 2017-18: January 8 and March 23

- Spring 2017-18: April 2 and June 13 (Commencement June 17)

- Summer 2017-18: June 25 and August 18

- Summer break: June 18-Sept 23, 2018

Tsinghua Calendar:

- Winter Break: 1/22-2/25 （2/16 Chinese New Year）

- Summer break, 7/2-9/16

- Chinese New Year: 1/28/2017

Peking University Calendar:

- Winter Break: 1/15-2/15

- Summer break, 7/2 – 9/10 (?)

University of Science and Technology of China:

- Winter Break: 1/20-2/14, 2018

- Summer break: ?